## Sheet1
EVENT MANAGER | Project Start Date
2025-05-26
Task | Start Date | End Date | Duration
 | time axis 2025-05-26 to 2025-08-11
Requirement & Planning
Gather feature requirements | 2025-05-26 | 2025-05-30 | 4
Create user flow diagrams | 2025-05-26 | 2025-05-28 | 2
Design wireframes for key screens | 2025-05-26 | 2025-05-30 | 4
Frontend Development
Build UI components with React.js | 2025-05-31 | 2025-06-02 | 2
Add filtering, search features | 2025-06-02 | 2025-06-06 | 4
Create admin dashboard | 2025-06-02 | 2025-06-07 | 5
DB & API Design
Design database schema | 2025-06-08 | 2025-06-12 | 4
Establish entity relationships | 2025-06-13 | 2025-06-14 | 1
Define API endpoints | 2025-06-15 | 2025-06-20 | 5
Backend Development
Integrate Node mailer with cron jobs | 2025-06-21 | 2025-06-26 | 5
Develop RESTful APIs for event CRUD | 2025-06-21 | 2025-06-26 | 5
Implement session-based authentication | 2025-06-27 | 2025-07-01 | 4
Integration & Testing
Connect frontend with backend APIs | 2025-07-02 | 2025-07-08 | 6
Test complete workflows | 2025-07-02 | 2025-07-16 | 14
Fix bugs and improve UX | 2025-07-15 | 2025-07-25 | 10
Final Deployment
Deploy frontend on Vercel | 2025-07-27 | 2025-08-01 | 5
Deploy backend on Render | 2025-07-27 | 2025-08-07 | 11
Final demo & presentation | 2025-08-11 | 2025-08-11 | 0 | bar: 2025-08-11